PlaceCom

Career Worksheet

# Proposal: Student-Led Career Navigation Worksheet

## Executive Summary

This proposal outlines a student-led initiative to design a Career Navigation Worksheet for Ashoka University undergraduates. The goal is to create a free, accessible resource that helps students structure their thinking regarding their first career steps post-graduation.

## Problem Statement

Many students approach their final year with anxiety and a lack of clarity regarding their career trajectory. While the Career Development Office (CDO) offers counseling, students often lack a tangible, self-guided framework to organize their thoughts, research, and action plans independently.

## Proposed Solution

We propose a comprehensive worksheet designed by students, for students. It will guide users through:

- Self-Reflection: Identifying core values, strengths, and interests

- Market Research: Frameworks for analyzing industries and roles

- Gap Analysis: Identifying skills needed vs. skills possessed

- Action Planning: Setting a timeline for applications and networking

## Implementation Plan

Team Structure The project will be executed by a volunteer team of 3-5 students, supervised by a representative from the CDO or a faculty mentor to ensure quality.

Cost There is zero financial cost associated with this project. It relies entirely on student time, existing digital tools (Canva/Google Docs), and university distribution channels.

Timeline (6 Weeks)

- Weeks 1-2: Student team formation and content research

- Weeks 3-4: Drafting and design

- Week 5: Review by CDO/Faculty and minor edits

- Week 6: Digital launch and distribution

## Potential Drawbacks & Risks

While this project is low-risk due to zero cost, there are potential challenges to consider:

- Low Engagement: Without mandatory integration into a course or workshop, students may download the file but never complete it.

- Lack of Expertise: Since it is designed by students, the advice may lack the depth or professional nuance that a certified career counselor would provide.

- One-Size-Fits-All Limitations: A single worksheet may struggle to cater to the diverse needs of all majors (e.g., a Computer Science student needs different prep than a Liberal Arts student).

## Conclusion

This initiative offers a high-value, low-effort solution to a common student problem. By leveraging student talent, we can create a relatable and useful tool that complements existing career services at no cost to the university.